# Chatbot Builder Application

Project Plan Document

Prepared by: Team Byte Squad

- Ashmit Nirwan

- Jordan Spector

- Gio Mendoza

- Milton Mupfumira

Course: Software Engineering
Date: April 2026

# 1. Introduction

This document outlines the project plan for the development of the Chatbot Builder Application. The purpose of this plan is to define the project scope, schedule, roles, and deliverables to ensure successful completion of the system within the academic timeline.

The Chatbot Builder Application is designed to allow users to create, test, and deploy AI-powered chatbots without requiring advanced programming knowledge. The system integrates frontend user interfaces, backend APIs, database storage, and AI-based response generation.

# 2. Project Objectives

The main objectives of the project are:

- Develop a user-friendly chatbot creation platform

- Enable chatbot creation without coding

- Support multiple knowledge sources (URL, text, PDF)

- Provide chatbot testing before deployment

- Allow chatbot publishing and public access

- Track chatbot usage through analytics

- Demonstrate full software engineering lifecycle

# 3. Scope of the Project

In Scope

- User authentication and role management

- Chatbot creation wizard

- Knowledge ingestion (text and URL)

- Chatbot testing interface

- Chatbot publishing and public access

- Analytics dashboard

- Admin features (password reset, analytics view)

- Git-based deployment workflow

Out of Scope

- Full production deployment (cloud hosting)

- Large-scale performance testing

- Advanced AI training beyond API usage

- Enterprise-level security features

# 4. Project Phases

The project is divided into the following phases:

Phase 1: Planning

- Requirement gathering

- User stories creation

- Product backlog definition

- Initial system design

Phase 2: Design

- UI/UX design (Figma concepts)

- System architecture design

- Database schema design

- UML diagrams

Phase 3: Development

- Frontend implementation (HTML, CSS, JavaScript)

- Backend development (Spring Boot APIs)

- Database integration (PostgreSQL)

- OpenAI API integration

- Git branching workflow setup

Phase 4: Testing

- Functional testing

- Integration testing

- API testing using Postman

- UI validation

- Bug fixing

Phase 5: Deployment & Demo

- Production profile setup

- Batch script for demo execution

- Final documentation

- Project presentation

# 5. Project Timeline (Jan 30 – April 17, 2026)

The project was executed in multiple phases over the semester, progressing from planning and design to development, integration, testing, and finalization.

Phase 1: Project Initiation & Planning (Jan 30 – Feb 7)

- Team formation and initial meetings

- Brainstorming project ideas and selecting chatbot builder concept

- Identification of roles and responsibilities

- Initial requirement discussions and workflow planning

Focus:

- Understanding project scope

- Defining high-level system idea

Phase 2: UI Design & Requirement Definition (Feb 8 – Feb 28)

- Creation of UI wireframes using Figma

- Design of dashboard, chatbot builder, and chat interface

- Development of user stories, use cases, and acceptance criteria

- Refinement of system workflow and user experience

Focus:

- Led UI design and user flow planning

- Refined project scope and usability

Phase 3: System Design & Documentation (Mar 1 – Mar 22)

- Creation of UML diagrams (class, sequence)

- Architecture design (logical and physical)

- Refinement of product backlog and requirements

- Alignment of UI with system functionality

Focus:

- Translating design into implementable structure

- Preparing for development

Phase 4: Development Phase (Mar 23 – Apr 5)

- Frontend development (dashboard, chatbot creation, analytics)

- Backend API development and integration

- Database schema implementation (User, Bot, BotChunk, etc.)

- Initial chatbot response logic implementation

Focus:

- UI implementation, frontend-backend alignment, API testing

- Backend development and API design

- UI refinement and feature structuring

Team Progress:

- Transition from design → working application

Phase 5: Integration & Testing (Apr 6 – Apr 12)

- Integration of frontend with backend APIs

- Chatbot testing using Postman and UI

- Debugging chatbot responses and fallback issues

- Analytics improvements and data visualization refinement

- Exploration of ChatGPT API integration

Focus

- API integration, analytics refinement, chatbot testing

- UI polish and system refinement

Phase 6: Finalization & Demo Preparation (Apr 13 – Apr 17)

- Completion of frontend-backend integration

- Replacement of static data with dynamic API responses

- Final UI refinement and usability improvements

- Completion of documentation (SRS, UML, Testing, Architecture)

- Preparation of demo environment and batch startup script

Focus:

- System stabilization

- Documentation completion

- Demo readiness

# 6. Team Roles and Responsibilities

| Team Member | Responsibilities |
| --- | --- |
| Ashmit Nirwan | UI design, frontend implementation, database design, AI integration, chatbot testing |
| Jordan Spector | Backend development, API integration, system logic |
| Gio Mendoza | UI enhancements, styling, testing, validation |
| Milton Mupfumira | Project planning, documentation, requirement tracking |

# 7. Tools and Technologies

| Category | Tools |
| --- | --- |
| Frontend | HTML, CSS, JavaScript |
| Backend | Spring Boot (Java) |
| Database | PostgreSQL |
| AI Integration | OpenAI API |
| Design | Figma |
| Version Control | Git, GitHub |
| Testing | Postman, Browser Testing |
| IDE | Eclipse |

# 8. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| OpenAI API dependency | High | Use fallback responses |
| Chunking limitations | Medium | Improve chunking strategy |
| Data inconsistency in analytics | Medium | Validate database queries |
| Git conflicts during merging | Medium | Follow structured workflow |
| Time constraints | High | Prioritize core features |

# 9. Deliverables

The project deliverables include:

- Software Requirements Specification (SRS)

- Product Backlog

- User Stories

- Use Case Document

- UML Diagrams

- Architecture Document

- Test Plan, Scripts, and Results

- Project Plan

- Git Workflow Documentation

- Production Gaps Document

- Final Demo Application

- Project Presentation

# 10. Project Workflow (Git Strategy)

The project follows a structured Git workflow:

Development

git checkout develop

git pull origin develop

Commit Changes

git add .

git commit -m "Working Code"

git push origin develop

Promote to Test

git checkout test

git pull origin test

git merge develop

git push origin test

Promote to Production

git checkout main

git pull origin main

git merge test

git push origin main

# 11. Success Criteria

The project will be considered successful if:

- All major features are implemented

- Users can create and deploy chatbots

- Chatbot responses are generated correctly for supported queries

- Analytics display meaningful data

- System runs successfully in demo mode

- Documentation is complete and organized

# 12. Conclusion

This project plan provides a structured approach to developing the Chatbot Builder Application. By following defined phases, responsibilities, and workflows, the team ensures systematic progress and successful delivery of a functional chatbot platform.